## Sheet1
Website Redesign Project Plan
Project Overview:
Client: Jake Rosen Entertainment (JRE)
Goal: Redesign website with a professional, modern vibe including new interactive elements like a 4K video landing page, dynamic sections (brands, creators), and a requestable talent roster.
Discovery and Research Phase (Week 1)
Task | Assigned To | Due Date | Notes
Initial Client Call & Requirement Gathering | Mewtwo | Day 1 | Clarify goals, structure, and specific requirements.
Competitor Research (Paul’s, Open Influence) | Mewtwo, Brock | Day 3 | Gather insights on similar websites and design trends.
Finalizing Client Preferences and Deliverables | Mewtwo, Client | Day 5 | Ensure agreement on structure, design, and content.
Design Phase (Week 2 - Week 3)
Task | Assigned To | Due Date | Notes
Create Mockups for Homepage (Video Landing Page, Numbers Section) | Brock | Day 7 | Align with client’s desired modern and professional vibe.
Design Interactive Features (Scrolling Numbers, Video Integration) | Brock | Day 10 | Create mockups for the video and numbers sections.
Review & Approval of Mockups | Mewtwo, Client | Day 12 | Client reviews and approves mockups.
Development Phase (Week 4 - Week 6)
Task | Assigned To | Due Date | Notes
Front-End Development (Video Landing Page, Scrolling Numbers, Navigation) | Ash | Day 15 | Implement front-end features based on approved mockups.
Back-End Development (Requestable Roster, Dynamic Data Integration | Misty | Day 16 | Integrate interactive features like the roster and data.
Integrate Content (Text, Testimonials, Portfolio) | External Copywriter | Day 17 | Integrate copy and content to match design.
Testing Front-End & Back-End (Functionality & Performance) | Ash, Misty | Day 20 | Ensure all interactive elements and pages work as expected.
Testing Phase (Week 7)
Task | Assigned To | Due Date | Notes
Usability Testing (Navigation, User Flow, Interactive Elements) | Mewtwo, Brock | Day 21 | Ensure easy navigation and smooth user experience.
Mobile Responsiveness Testing | Ash, Misty | Day 22 | Ensure the website is fully responsive across devices.
Performance Testing (Video Quality, Speed, Load Time) | Ash, Misty | Day 23 | Ensure smooth video loading and fast page load times.
Final Client Review (Website Demo on Staging Server) | Mewtwo, Client | Day 24 | Client final review and feedback.
Deployment Phase (Week 8)
Task | Assigned To | Due Date | Notes
Deploy Website to Live Server | Ash, Misty | Day 25 | Final deployment after approval.
Post-launch Support and Bug Fixes | Mewtwo, Ash, Misty | Day 26-28 | Address any bugs or issues post-launch.
Final Client Handover & Documentation | Mewtwo | Day 28 | Provide all necessary documentation and handover to the client.